## List of Partners
Partner N° | Partner Name | Partner Short Name | Type of Partner | Country | Country Code | Region | Academic Sector | PIC Number
1 | Université de Liége | ULIEGE | Beneficiary | Belgium | BE | EU/AC | Yes | 999976105
2 | Universidad de O´Higgins | UOH | Third Country | Chile | CL | TC | Yes | 905358231
3 | Institut Agronomique et Vétérinaire Hassan II | IAV | Third Country | Morocco | MA | TC | Yes | 998781744
4 | Institut National de la Recherche Agronomique | INRA | Third Country | Morocco | MA | TC | Yes | 997320148
5 | Instituto de Recursos Naturales y Agrobiología de Sevilla | IRNAS | Beneficiary | Spain | ES | EU/AC | Yes | 908879913
6 | Universita degli Studi di Firenze | UNIFI | Beneficiary | Italy | IT | EU/AC | Yes | 999895789
7 | University of Chile | UCHILE | Third Country | Chile | CL | TC | Yes | 999447067
8 | Luxembourg Institute of Science ad Technology | LIST | Beneficiary | Luxembourg | LU | EU/AC | Yes | 934320200
9 | Agroptimize | AGROP | Beneficiary | Belgique | BE | EU/AC | No | 894501894
10 | Auravant | AURA | Third Country | Argentine | AR | TC | No | 894281607
11 | Initiative AAA | IAAA | Third Country | Morocco | MA | TC | Yes | 894632844
12 | Universita di Bologna | UNIBO | Beneficiary | Italy | IT | EU/AC | Yes | 999993953
13 | Institut Agro Montpellier | IA | Beneficiary | France | FR | EU/AC | Yes | 895461515

## Staff
ID | Name | Institution | Profile | WPs to be involved | e-mail
1 | Abir LEMSEFFER | IAAA | ER | 3 | abirlemseffer@gmail.com
2 | Faouzi BEKKAOUI | IAAA | ER | 3 | faouzi.bekkaoui@gmail.com
3 | Loubna CHAMIM | IAAA | ER | 2 , 5 | chamimloubna@gmail.com
4 | Mohamed AIT KADI | IAAA | ER | 5 , 6 | aitkadi.med@gmail.com
5 | Nezha MOUCHFI | IAAA | ER | 4 , 5 | mouchfin@gmail.com
6 | Riad BALAGHI | IAAA | ER | 6 | riad.balaghi@aaainitiative.org
1 | BOUAZIZ Ahmed | IAV | ER | 3 , 4 | a.bouaziz@iav.ac.ma
2 | Brahim Soudi | IAV | ER | 6 | b.soudi@iav.ac.ma
3 | Ehssan EL MEKNASSI YOUSSOUFI | IAV | ER | 3 , 4 | e.elmeknassi@iav.ac.ma
4 | Lahoussaine Baamal | IAV | ER | 2 | l.baamal@iav.ac.ma
5 | Mohamed Moulay Ajerame | IAV | ER | 4 | m.ajerame@iav.ac.ma
6 | Mohammed DEHHAOUI | IAV | ER | 4 | m.dehhaoui@iav.ac.ma
7 | Mouanis LAHLOU | IAV | ER | 4 , 5 | m.lahlou@iav.ac.ma
8 | Mourad Bouziani | IAV | ER | 1 , 7 | m.bouziani@iav.ac.ma
9 | Nouredine Chtaina | IAV | ER | 3 | n.chtaina@iav.ac.ma
10 | Ouiam LAHLOU | IAV | ER | 5 | o.lahlou@iav.ac.ma
11 | Sanaa Zebakh | IAV | ER | 2 | sanaa.zebakh@yahoo.com
12 | Nassreddine MAATALA | IAV | ER | 6 | m.nassreddine@gmail.com
13 | Pd. D. 1 | IAV | ESR | 6
14 | Ph. D. 2 | IAV | ESR | 6
15 | Ph. D. 3 | IAV | ESR
16 | TTO | IAV | MNG
1 | Hamid Mahyou | INRA-M | ER | 5, 6, 7 | mahyouh@yahoo.com
2 | Hassan Benaouda | INRA-M | ER | 5, 7 | hbenaouda_inra@yahoo.fr
3 | Karim Andich | INRA-M | ER | 3 | andichkarim@gmail.com
4 | Khalid Khfif | INRA-M | ER | 4 | khalild3@hotmail.com
5 | Rachid Hadria | INRA-M | ER | 2 | r.hadria@gmail.com
6 | Reda Meziani | INRA-M | ER | 3.7 | redameziani@yahoo.fr
7 | Wadii Snaibi | INRA-M | ER | 6, 7 | snaibi.wadii@gmail.com
8 | Zineb Belabess | INRA-M | ER | 4 | belabess.zineb@gmail.com
1 | Heike Knicker | IRNAS | ER | 3 | knicker@irnase.csic.es
2 | Rafael Lopez | IRNAS | ER | 3 | rafael.lopez@csic.es
3 | Not determined | IRNAS | ESR | 3
4 | Jose Antonio Gonzalez Perez | IRNAS | ER | 3 | jag@irnase.csic.es
5 | Not determined | IRNAS | ESR | 3
6 | Marta Velasco Molina | IRNAS | TECH | 3 | m.velasco@irnas.csic.es
7 | Jose Maria de la Rosa | IRNAS | ER | 3 | jmrosa@irnase.csic.es
1 | Lucien Hoffmann | LIST | ER | 6 | lucien.hoffmann@list.lu
1 | Fabian Medel | UCHILE | ER | 2, 5 | fmedel@dim.uchile.cl
2 | Fernando Ordóñez | UCHILE | ER | 6 | fordon@dii.uchile.cl
3 | Gerardo Soto M. | UCHILE | ER | 3 | gerardo.soto@renare.uchile.cl
4 | Giorgio Castellaro G | UCHILE | ER | 5 | gicastel@uchile.cl
5 | Jaime Ortega | UCHILE | ER | 2, 5 | jortega@dim.uchile.cl
6 | Luis Morales | UCHILE | ER | 5 | lmorales@uchile.cl
7 | Mauricio Galleguillos | UCHILE | ER | 2 | mgalleguillos@renare.uchile.cl
8 | Sebastían Ríos | UCHILE | ER | 6 | srios@dii.uchile.cl
9 | Director Open Beaucheff | UCHILE | MNG | 7
10 | Ph. D. 1 | UCHILE | ESR | 2
11 | Ph. D. 2 | UCHILE | ESR | 6
12 | Ph. D. 3 | UCHILE | ESR | 5
10 | CFO CMM | UCHILE | MNG | 1
1 | Bernard Tychon | ULIEGE | ER | 5 | Bernard.Tychon@uliege.be
2 | Eric Feller | ULIEGE | ER | 7 | e.feller@uliege.be
3 | Mousse El Jarroudi | ULIEGE | ER | 4 | meljarroudi@uliege.be
4 | Bernard Tychon | ULIEGE | ER | 5 | Bernard.Tychon@uliege.be
5 | Joost Wellens | ULIEGE | ER | 2, 5 | Joost.Wellens@uliege.be
6 | Pierre Ozer | ULIEGE | ER | 6 | pozer@uliege.be
7 | Hugues Jupsin | ULIEGE | ER | 2 | h.jupsin@ulg.ac.be
8 | Philippe Lebailly | ULIEGE | ER | 6 | philippe.lebailly@uliege.be
9 | Monique Carnol | ULIEGE | ER |  | m.carnol@uliege.be
10 | Marie Lang | ULIEGE | ER |  | marie.lang@uliege.be
11 | Denis Antoine | ULIEGE | ER |  | Antoine.Denis@uliege.be
12 | Ph. D. 1 | ULIEGE | ESR
13 | Ph. D. 2 | ULIEGE | ESR
14 | Ph. D. 3 | ULIEGE | ESR
15 | TTO 1 | ULIEGE | MNG
16 | TTO 2 | ULIEGE | MNG
17 | TTO 3 | ULIEGE | MNG
1 | Antonio Prodi | UNIBO | ER | 4 | antonio.prodi@unibo.it
2 | Chiara Lanzoni | UNIBO | ER | 4 | chiara.lanzoni4@unibo.it
3 | Claudio Ratti | UNIBO | ER | 4 | claudio.ratti@unibo.it
4 | David Baldo | UNIBO | ER | 4 | david.baldo2@unibo.it
5 | Eleonora Cappelletti | UNIBO | ER | 4 | eleonora.cappellett5@unibo.it
6 | Enrico Biondi | UNIBO | ER | 4 | enrico.biondi3@unibo.it
7 | Maria Rita Proto | UNIBO | ER | 4 | mariarita.proto2@unibo.it
8 | Maria Teresa Senatore | UNIBO | ER | 4 | mariateresa.senatore@unibo.it
9 | Mattia Dall'Ara | UNIBO | ER | 4 | mattia.dallara5@unibo.it
10 | Paola Minardi | UNIBO | ER | 4 | paola.minardi@unibo.it
11 | Antonio Masetti | UNIBO | ER | 4 | antonio.masetti@unibo.it
12 | Laura Depalo | UNIBO | ER | 4 | laura.depalo@unibo.it
13 | Serena Magagnoli | UNIBO | ER | 4 | serena.magagnoli4@unibo.it
14 | Post Doc 1 | UNIBO | ER
15 | Post Doc 2 | UNIBO | ER
1 | Massimo Delbubba | UNIFI | ER | 2 | massimo.delbubba@unifi.it
2 | Ayoub El Ghadraoui | UNIFI | ER | 2 | ayoub.elghadraoui@unifi.it
1 | Claudia Rojas | UOH | ER | 3 | claudia.rojas@uoh.cl
2 | Cristóbal Quiñinao | UOH | ER | 4, 5 | cristobal.quininao@uoh.cl
3 | Diego Muñoz | UOH | ER | 2, 5 | diego.munoz@uoh.cl
4 | Florencio Utreras | UOH | MNG | 1, 7 | florencio.utreras@uoh.cl
5 | Jorge Medina | UOH | ER | 3 | jorge.medina@uoh.cl
6 | Lorena Pizarro | UOH | ER | 3, 4 | lorena.pizarro@uoh.cl
7 | Mauricio Latorre | UOH | ER | 3, 4 | mauricio.latorre@uoh.cl
8 | Miguel Torres | UOH | ER | 6 | miguel.torres@uoh.cl
9 | Pablo Gutiérrez | UOH | ER | 5 | pablo.gutierrze@uoh.cl
10 | Paula Irles | UOH | ER | 4 | paula.irles@uoh.cl
11 | Pedro Pérez | UOH | ER | 2 | pedro.perez@uoh.cl
12 | Raúl Valenzuela | UOH | ER | 5, 6 | raul.valenzuela@uoh.cl
13 | Rodrigo Contreras | UOH | ER | 3 | rodrigo.contreras@uoh.cl
14 | Rodrigo Verschae | UOH | ER | 4, 5, 6 | rodrigo.verschae@uoh.cl
15 | Set Pérez | UOH | ER | 4 | set.perez@uoh.cl
16 | Víctor Verdugo | UOH | ER | 5, 6 | victor.verdugo@uoh.cl
17 | PostDoc Suelos 1 | UOH | ER | 3
18 | PostDoc Suelos 2 | UOH | ER | 3
19 | Pilar Fuenzalida | UOH | TECH | 3 | pilar.fuenzalida@uoh.cl
20 | PostDoc Agua 1 | UOH | ER | 2
21 | PostDoc Agua 2 | UOH | ER
21 | Post Doc Patógenos 1 | UOH | ER | 4
22 | Post Doc Patógenos 2 | UOH | ER | 4
23 | Post Doc Agrometeorologia 1 | UOH | ER | 5
24 | Post Doc Agrometeorologia 2 | UOH | ER | 5
25 | Post Doc Riesgo 1 | UOH | ER | 6
26 | Post Doc Riesgo 2 | UOH | ER | 6
27 | Post Doc Riesgo 3 | UOH | ER | 6
28 |  | UOH | ER
23 | Vicerrector | UOH | MNG | 1, 7
24 | Director of Research | UOH | MNG | 1, 7
25 | CFO UOH | UOH | MNG | 1
1 | Timothee Barbier | AGROP | MNG | 5, 7
2 | Business Devlopper | AGROP | TECH | 7
3 |  | AGROP
4 |  | AGROP
1 | Nicolás Larrandart | AURA | TECH | 3, 4, 5 | nicolas@auravant.com
2 | Rodrigo Aime | AURA | TECH | 3 | rodrigo.aime@auravant.com
3 | Alvaro Buteler | AURA | TECH | 5 | alvaro.buteler@auravant.com
4 | Rodrigo Carrizo | AURA | TECH | 5 | rodrigo.carrizo@auravant.com
5 | Fernando Calo | AURA | TECH | 4 | fernando.calo@auravant.com
6 | Agustín Michlig | AURA | TECH | 1, 2, 3, 4, 5, 6, 7 | agustín.michlig@auravant.com
7 | Virginia Passaniti | AURA | TECH | 4, 3 | virginia.passaniti@auravant.com
8 | Facundo Ferrín | AURA | TECH | 2, 5 | facundo.ferrín@auravant.com
1 | Armand Crabit | SUPAGRO | ESR | 2 | armand.crabit@supagro.fr

## Summary WPs
Do not complete cases in red
Work Package No | Work Package Title | Activity Type (e.g. Research, Training, Management, Communication, Dissemination…) | Number of person-months involved per secondment | Lead Beneficiary | Start Month | End Month
1 | Management | Management | 0 | #NAME? | 1 | 36
2 | Recycled water and sustainable management | Research & Training | 0 | #NAME? | 0 | 0
3 | Sustainable soil management | Research & Training | 0 | #NAME? | 3 | 28
4 | Smart farming for crop protection | Research & Training | 0 | #NAME? | 1 | 30
5 | Modeling crops and pasture as a tool for a more resilient agriculture | Research & Training | 0 | #NAME? | 3 | 36
6 | Risk Management in Agriculture | Research & Training | 0 | #NAME? | 8 | 32
7 | Dissemination & Innovation | Dissemination | 0 | #NAME? | 0 | 33
Totals |  |  | 0 |  | 0 | 36

## EC Clssification Types
Partner Classification
MS/AC | Member State/Associated Country
TC | Third Country
Staff Classification
ER | Experienced Researcher
ESR | Early Stage Researcher
MNG | Manager
ADM | Administrative
TECH | Technician
Deliverables Classification
R | Document, report (excluding periodic and final reports)
ADM | Administrative (ethics/legal/administrative related outputs);
PDE | dissemination and/or exploitation of project results (website completion, patents filing, conference, etc.)
OTHER | Other, including coordination
Deliverables Dissemination Level
PU | Public: fully open, e.g. web
CO | Confidential: restricted to consortium, other designated entities (as appropriate) and Commission services; Important: please note that upon approval by the REA Project Officer, the deliverables with Public dissemination level (PU) will be automatically published on CORDIS, the European Commission's primary portal for results of EU-funded research projects. Therefore, make sure the content is appropriate both in terms of quality and confidentiality.
CI | Classified: classified information as intended in Commission Decision 2001/844/EC.

## Deliverables
This Worksheet is automatically completed once each Deliverable list is built in each WP
Scientific Deliverables | [6 empty] | Management, Training, and Dissemination Deliverables
Deliverable Number | Deliverable Title | WP No. | Lead Beneficiary Short Name | Type | Dissemination Level | Due Date | Deliverable Number | Deliverable Title | WP No. | Lead Beneficiary Short Name | Type | Dissemination Level | Due Date
D2.1 | 0 | 2 | 0 | 0 | 0 | 0 | D1.1 | 0 | 1 | 0 | 0 | 0 | 0
D2.2 | 0 | 2 | 0 | 0 | 0 | 0 | D1.2 | 0 | 1 | 0 | 0 | 0 | 0
D2.3 | 0 | 2 | 0 | 0 | 0 | 0 | D1.3 | 0 | 1 | 0 | 0 | 0 | 0
D2.4 | 0 | 2 | 0 | 0 | 0 | 0 | D1.4 | 0 | 1 | 0 | 0 | 0 | 0
D2.5 | 0 | 2 | 0 | 0 | 0 | 0 | D1.5 | 0 | 1 | 0 | 0 | 0 | 0
D2.6 | 0 | 2 | 0 | 0 | 0 | 0 | D1.6 | 0 | 1 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D3.1 | (R) 3 publications oriented to the academy on the interaction between climatic condition, soil degradation, management and greenhouse gas production | 3 | IRNAS | R | PU | 18, 24,36 | D7.1 | Project’s Website. | 7 | ULIEGE | OTHER | PU | 4
D3.2 | (R) 3 scientific publications oriented to the academy with main results on soil responses to organic amendments in degraded soils and soils at risk under climate change conditions (M34) | 3 | IRNAS | 0 | 0 | 24.36 | D7.2 | Dissemination Activities Report I | 7 | ULIEGE | R | PU | 12
D3.3 | (R) technical report oriented to farmers, local managers and other stakeholders with the main results and recommendations on sustainable soil management practices (M36) | 3 | IRNAS | 0 | 0 | 36 | D7.3 | Dissemination Activities Report II | 7 | ULIEGE | R | PU | 25
D3.4 | (PDE) website hosting project description, open access graphical information (soil map) generated in the project and main results and recommendations on sustainable soil management practices (36) | 3 | IRNAS | 0 | 0 | 3, 24, 36 | D7.4 | Dissemination Activities Report III | 7 | ULIEGE | R | PU | 36
D3.5 | (PDE) Training school in Spain on cutting edge techniques and analytical tools for soil organic matter analysis experience gained in the project | 3 | IRNAS | R | PU | 12 | D7.5 | Regulations for a Resilient Agriculture: Comparative Study | 7 | ULIEGE | R | PU | 23
D3.6 | (PDE) workshop in Morocco to disseminate knowledge and experience gained in the project | 3 | IRNAS | R | PU | 24 | D7.6 | An Open Innovation Strategy for a Resilient Agricuture | 7 | ULIEGE | R | PU | 33
D3.7 | (PDE) workshop in Chile to disseminate knowledge and experience gained in the project | 3 | IRNAS | R | PU | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D4.1 | Open field training for plant sample collection, processing and storage at each beneficiary location of WP4 | 4 | 0 | PDE | 0 | 0
D4.2 | Training on sample processing for the detection of plant pathogens and pests | 4 | 0 | PDE | 0 | 0
D4.3 | Training on detection and identification of plant pathogen and pests through novel, rapid and sensitive molecular methods | 4 | 0 | PDE | 0 | 0
D4.4 | Training on in vitro experiments (by diffusion, micro- and macro-dilution | 4 | 0 | PDE | 0 | 0
D4.5 | 0 | 4 | 0 | 0 | 0 | 0
D4.6 | 0 | 4 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
D5.1 | Updated crop and pasture yield and production systems for at least 2 countries | 5 | ULIEGE | R | PU | 0
D5.2 | Report on the climate change and economy context change impacts on resilience of agriculture for at least two countries in semi-arid areas | 5 | ULIEGE | R | PU | 0
D5.3 | Workshop on ... | 5 | ULIEGE | PDE | PU | 0
D5.4 | Workshop on ... | 5 | ULIEGE | PDE | PU | 0
D5.5 | Training course on ... | 5 | ULIEGE | PDE | PU | 0
D5.6 | Training course on ... | 5 | ULIEGE | PDE | PU | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
D6.1 | Methods and tools to improve the assessment and forecasting of production risks taken by farmers | 6 | 0 | R | PU | 0
D6.2 | Methods and tools to reduce/mitigate production risks | 6 | 0 | R | PU | 0
D6.3 | Agriculture Risk Management | 6 | 0 | R | PU | 0
D6.4 | Workshop on… | 6 | 0 | PDE | PU | 0
D6.5 | Workshop on… | 6 | 0 | PDE | PU | 0
D6.6 | Training Course | 6 | 0 | PDE | PU | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0

## Milestones
Number | Title | Related WPs | Lead Beneficiary | Due Date | Means of Verification

## Risk List
Risk No | Description of Risk | WP Number | Proposed mitigation measures

## WP1
| Workpackage Number |  | 1
| Task N° | Task Name | Leading Partner | Staff ID | Sending Institution | Seconded to Organisation | Secondment Starting Month | Secondment Duration | Secondment Ends
| Task 1.1 | Coordination | ULIEGE | 1 | UOH | ULIEGE | 1 | 1 | 1
|  |  |  | 5 | UCHILE | ULIEGE | 1 | 1 | 1
|  |  |  | 1 | AURA | ULIEGE | 1 | 1 | 1
|  |  |  | 1 | IAAA | ULIEGE | 1 | 1 | 1
|  |  |  | 1 | INRA | ULIEGE | 1 | 1 | 1
|  |  |  | 1 | UAV | ULIEGE | 1 | 1 | 1
|  |  |  | 1 | UOH | ULIEGE | 13 | 1 | 13
|  |  |  | 5 | UCHILE | ULIEGE | 13 | 1 | 13
|  |  |  | 1 | AURA | ULIEGE | 13 | 1 | 13
|  |  |  | 1 | IAAA | ULIEGE | 13 | 1 | 13
|  |  |  | 1 | INRA | ULIEGE | 13 | 1 | 13
|  |  |  | 1 | UAV | ULIEGE | 13 | 1 | 13
|  |  |  | 1 | UOH | ULIEGE | 25 | 1 | 25
|  |  |  | 5 | UCHILE | ULIEGE | 25 | 1 | 25
|  |  |  | 1 | AURA | ULIEGE | 25 | 1 | 25
|  |  |  | 1 | IAAA | ULIEGE | 25 | 1 | 25
|  |  |  | 1 | INRA | ULIEGE | 25 | 1 | 25
|  |  |  | 1 | UAV | ULIEGE | 25 | 1 | 25
|  |  |  | 1 | UOH | ULIEGE | 36 | 1 | 36
|  |  |  | 5 | UCHILE | ULIEGE | 36 | 1 | 36
|  |  |  | 1 | AURA | ULIEGE | 36 | 1 | 36
|  |  |  | 1 | IAAA | ULIEGE | 36 | 1 | 36
|  |  |  | 1 | INRA | ULIEGE | 36 | 1 | 36
|  |  |  | 1 | UAV | ULIEGE | 36 | 1 | 36
| Summary | Task 1.1 |  |  |  |  | 1 | 24 | 36
| Task 1.2 | Financial Administration | ULIEGE | 25 | UOH | ULIEGE | 1 | 1 | 1
|  |  |  | 10 | UCHILE | ULIEGE | 1 | 1 | 1
|  |  |  | 1 | AURA | ULIEGE | 1 | 1 | 1
|  |  |  | 1 | IAAA | ULIEGE | 1 | 1 | 1
|  |  |  | 1 | INRA | ULIEGE | 1 | 1 | 1
|  |  |  | 1 | UAV | ULIEGE | 1 | 1 | 1
| Summary | Task 1.2 |  |  |  |  | 1 | 6 | 1
| Task 1.3 | Deliverables, Milestones and Indicators control | ULIEGE | 1 | ULIEGE | UOH | 6 | 1 | 6
|  |  |  | 1 | ULIEGE | IAV | 18 | 1 | 18
|  |  |  | 1 | ULIEGE | AURA | 30 | 1 | 30
| Summary | Task 1.3 |  |  |  |  | 6 | 3 | 30
| Participating organisation Short Name |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Total Person Months per Participating organisation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary of Tasks Workpackage Number 1
| Task # | Task Name | Starting Month | End Month | PMs per Task
1 | Task 1.1 | Coordination | 1 | 36 | 24 |  | This table is automatically completed once the list of Tasks is entered
2 | Task 1.2 | Financial Administration | 1 | 1 | 6
3 | Task 1.3 | Deliverables, Milestones and Indicators control | 6 | 30 | 3
3
3
| Totals WP per Task |  | 1 | 36 | 33
| Total Tasks Workpackage Number 1 |  | 3
List of Deliverables
| Deliverable Number | Deliverable Title | WP No. | Lead Beneficiary Short Name | Type | Dissemination Level | Due Date
1 | D1.1 |  | 1
2 | D1.2 |  | 1
3 | D1.3 |  | 1
4 | D1.4 |  | 1
5 | D1.5 |  | 1
6 | D1.6 |  | 1
7
8
9
10

## WP2
| Workpackage Number |  | 2
| Task N° | Task Name | Leading Partner | Staff ID | Sending Institution | Seconded to Organisation | Secondment Starting Month | Secondment Duration | Secondment Ends
| Task 2.1 | Production and characterization of sludge-based biochar, and its use in constructed wetland pilot systems | UNIFI
| Summary | Task 2.1 |  |  |  |  | 0 | 0 | 0
| Task 2.2 | Analysis and monitoring of the system efficiency and the water quality | UNIFI
| Summary | Task 2.2 |  |  |  |  | 0 | 0 | 0
| Task 2.3 | Food analysis for the assessment of food safety and quality | UNIFI
| Summary | Task 2.3 |  |  |  |  | 0 | 0 | 0
| Task 2.4 | Development of mathematical models for optimization involving uncertainty for recycled water and sustainable water management with a focus on irrigation use | UOH
| Summary | Task 2.4 |  |  |  |  | 0 | 0 | 0
| Task 2.5 | Development of stochastic optimal control schemes for management recycled water and sustainable water management for irrigation use | UOH
| Summary | Task 2.5 |  |  |  |  | 0 | 0 | 0
| Participating organisation Short Name |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Total Person Months per Participating organisation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary of Tasks Workpackage Number 2
| Task # | Task Name | Starting Month | End Month | PMs per Task
1 | Task 2.1 | Production and characterization of sludge-based biochar, and its use in constructed wetland pilot systems | 0 | 0 | 0 |  |  | This table is automatically completed once the list of Tasks is entered
2 | Task 2.2 | Analysis and monitoring of the system efficiency and the water quality | 0 | 0 | 0
3 | Task 2.3 | Food analysis for the assessment of food safety and quality | 0 | 0 | 0
4 | Task 2.4 | Development of mathematical models for optimization involving uncertainty for recycled water and sustainable water management with a focus on irrigation use | 0 | 0 | 0
5 | Task 2.5 | Development of stochastic optimal control schemes for management recycled water and sustainable water management for irrigation use | 0 | 0 | 0
| Totals WP per Task |  | 0 | 0 | 0
| Total Tasks Workpackage Number 2 |  | 5
List of Deliverables
| Deliverable Number | Deliverable Title | WP No. | Lead Beneficiary Short Name | Type | Dissemination Level | Due Date
1 | D2.1 |  | 2
2 | D2.2 |  | 2
3 | D2.3 |  | 2
4 | D2.4 |  | 2
5 | D2.5 |  | 2
6 | D2.6 |  | 2
7
8
9
10

## WP3
| Workpackage Number |  | 3
| Task N° | Task Name | Leading Partner | Staff ID | Sending Institution | Seconded to Organisation | Secondment Starting Month | Secondment Duration | Secondment Ends
| Task 3.1 | Selection and description of degraded soils | IRNAS | 1 | UOH | IRNAS | 3 | 1 | 3
|  |  |  | 1 | IRNAS | UOH | 6 | 1 | 6
|  |  |  | 3 | IRNAS | UOH | 6 | 3 | 8
|  |  |  | 1 | IRNAS | IAV | 4 | 1 | 4
|  |  |  | 3 | IRNAS | IAV | 4 | 1 | 4
|  |  |  | 6 | IRNAS | IAV | 4 | 1 | 4
|  |  |  | 6 | IRNAS | UOH | 6 | 1 | 6
| Summary | Task 3.1 |  |  |  |  | 3 | 9 | 8
| Task 3.2 | Mesocosms, greenhouse and field experiments with soil amendment monitoring | IRNAS | 5 | UOH | IRNAS | 12 | 3 | 14
|  |  |  | 17 | UOH | IRNAS | 12 | 6 | 17
|  |  |  | 18 | UOH | IRNAS | 12 | 6 | 17
|  |  |  | 19 | UOH | IRNAS | 12 | 6 | 17
|  |  |  | 5 | IRNAS | UOH | 17 | 3 | 19
|  |  |  | 2 | IRNAS | UOH | 17 | 1 | 17
|  |  |  | 7 | IRNAS | UOH | 17 | 1 | 17
|  |  |  | 5 | IRNAS | UNIBO | 6 | 1 | 6
| Summary | Task 3.2 |  |  |  |  | 6 | 27 | 19
| Task 3.3 | Robust multi-continental frame network collaboration | IRNAS | 1 | UOH | IRNAS | 18 | 1 | 18
|  |  |  | 5 | UOH | IRNAS | 18 | 1 | 18
|  |  |  | 17 | UOH | IRNAS | 18 | 1 | 18
|  |  |  | 18 | UOH | IRNAS | 18 | 1 | 18
|  |  |  | 4 | IRNAS | UOH | 17 | 1 | 17
|  |  |  | 3 | IRNAS | UOH | 28 | 1 | 28
|  |  |  | 1 | IRNAS | UAV | 30 | 1
| Summary | Task 3.3 |  |  |  |  | 17 | 7 | 28
| Participating organisation Short Name |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Total Person Months per Participating organisation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0
Summary of Tasks Workpackage Number 3
| Task # | Task Name | Starting Month | End Month | PMs per Task
1 | Task 3.1 | Selection and description of degraded soils | 3 | 8 | 9 |  |  | This table is automatically completed once the list of Tasks is entered
2 | Task 3.2 | Mesocosms, greenhouse and field experiments with soil amendment monitoring | 6 | 19 | 27
3 | Task 3.3 | Robust multi-continental frame network collaboration | 17 | 28 | 7
| Totals WP per Task |  | 3 | 28 | 43
| Total Tasks Workpackage Number 3 |  | 3
List of Deliverables
| Deliverable Number | Deliverable Title | WP No. | Lead Beneficiary Short Name | Type | Dissemination Level | Due Date
1 | D3.1 | (R) 3 publications oriented to the academy on the interaction between climatic condition, soil degradation, management and greenhouse gas production | 3 | IRNAS | R | PU | 18, 24,36
2 | D3.2 | (R) 3 scientific publications oriented to the academy with main results on soil responses to organic amendments in degraded soils and soils at risk under climate change conditions (M34) | 3 | IRNAS |  |  | 24.36
3 | D3.3 | (R) technical report oriented to farmers, local managers and other stakeholders with the main results and recommendations on sustainable soil management practices (M36) | 3 | IRNAS |  |  | 36
4 | D3.4 | (PDE) website hosting project description, open access graphical information (soil map) generated in the project and main results and recommendations on sustainable soil management practices (36) | 3 | IRNAS |  |  | 3, 24, 36
5 | D3.5 | (PDE) Training school in Spain on cutting edge techniques and analytical tools for soil organic matter analysis experience gained in the project | 3 | IRNAS | R | PU | 12
6 | D3.6 | (PDE) workshop in Morocco to disseminate knowledge and experience gained in the project | 3 | IRNAS | R | PU | 24
7 | D3.7 | (PDE) workshop in Chile to disseminate knowledge and experience gained in the project | 3 | IRNAS | R | PU | 30
8
9
10

## WP4
| Workpackage Number |  | 4
| Task N° | Task Name | Leading Partner | Staff ID | Sending Institution | Seconded to Organisation | Secondment Starting Month | Secondment Duration | Secondment Ends
| Task 4.1 | Monitoring of plant pathogens and pests: Diagnostics and Epidemiology | UNIBO | 1 | UNIBO | UOH | 1 | 1 | 1
|  |  |  | 3 | UNIBO | UOH | 1 | 1 | 1
|  |  |  | 6 | UNIBO | UOH | 1 | 1 | 1
|  |  |  | 8 | IAV | UOH | 1 | 1 | 1
|  |  |  | 8 | IAV | UOH | 6 | 1 | 6
|  |  |  | 2 | UOH | UNIBO | 29 | 1 | 29
| Summary | Task 4.1 |  |  |  |  | 1 | 6 | 29
| Task 4.2 | Pathogen detection and identification thorough novel molecular assays | UNIBO | 15 | UOH | UNIBO | 7 | 2 | 8
|  |  |  | 21 | UOH | UNIBO | 5 | 2 | 6
|  |  |  | 1 | IAV | UNIBO | 6 | 4 | 9
|  |  |  | 2 | IAV | UNIBO | 8 | 2 | 9
| Summary | Task 4.2 |  |  |  |  | 5 | 10 | 9
| Task 4.3 | Monitoring of plant pests: detection and identification |  | 11 | UNIBO | UOH | 1 | 1 | 1
|  |  |  | 11 | UNIBO | UOH | 1 | 1 | 1
|  |  |  | 10 | UOH | UNIBO | 6 | 2 | 7
|  |  |  | 10 | UOH | UNIBO | 29 | 1 | 29
|  |  |  | 14 | UOH | UNIBO | 19 | 1 | 19
|  |  |  | 4 | INRA | UOH | 6 | 1 | 6 | Not possible
|  |  |  | 2 | IAV | UNIBO | 12 | 2 | 13
|  |  |  | 4 | IAV | UNIBO | 18 | 2 | 19
| Summary | Task 4.3 |  |  |  |  | 1 | 11 | 29
| Task 4.4 | Integrated pathogen/pest management with biocontrol agents (BCA): sustainable control methods for a resilient agriculture | UNIBO | 1 | UNIBO | UOH | 24 | 1 | 24
|  |  |  | 3 | UNIBO | UOH | 24 | 1 | 24
|  |  |  | 6 | UNIBO | UOH | 24 | 1 | 24
|  |  |  | 2 | IAV | UNIBO | 12 | 2 | 13
|  |  |  | 2 | IAV | UNIBO | 12 | 2 | 13
|  |  |  | 15 | UOH | UNIBO | 29 | 2 | 30
|  |  |  | 20 | UOH | UNIBO | 5 | 2 | 6
|  |  |  | 4 | INRA | UOH | 24 | 1 | 24 | Not possible
|  |  |  | 8 | INRA | UOH | 24 | 1 | 24 | Not possible
|  |  |  | 8 | INRA | UOH | 30 | 1 | 30 | Not possible
|  |  |  | 4 | INRA | UOH | 30 | 1 | 30 | Not possible
| Summary | Task 4.4 |  |  |  |  | 5 | 15 | 30
| Participating organisation Short Name |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Total Person Months per Participating organisation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary of Tasks Workpackage Number 4
| Task # | Task Name | Starting Month | End Month | PMs per Task
1 | Task 4.1 | Monitoring of plant pathogens and pests: Diagnostics and Epidemiology | 1 | 29 | 6 |  |  | This table is automatically completed once the list of Tasks is entered
2 | Task 4.2 | Pathogen detection and identification thorough novel molecular assays | 5 | 9 | 10
3 | Task 4.3 | Monitoring of plant pests: detection and identification | 1 | 29 | 11
4 | Task 4.4 | Integrated pathogen/pest management with biocontrol agents (BCA): sustainable control methods for a resilient agriculture | 5 | 30 | 15
| Totals WP per Task |  | 1 | 30 | 42
| Total Tasks Workpackage Number 4 |  | 4
List of Deliverables
| Deliverable Number | Deliverable Title | WP No. | Lead Beneficiary Short Name | Type | Dissemination Level | Due Date
1 | D4.1 | Open field training for plant sample collection, processing and storage at each beneficiary location of WP4 | 4 |  | PDE
2 | D4.2 | Training on sample processing for the detection of plant pathogens and pests | 4 |  | PDE
3 | D4.3 | Training on detection and identification of plant pathogen and pests through novel, rapid and sensitive molecular methods | 4 |  | PDE
4 | D4.4 | Training on in vitro experiments (by diffusion, micro- and macro-dilution | 4 |  | PDE
5 | D4.5 |  | 4
6 | D4.6 |  | 4
7
8
9
10

## WP5
| Workpackage Number |  | 5
| Task N° | Task Name | Leading Partner | Staff ID | Sending Institution | Seconded to Organisation | Secondment Starting Month | Secondment Duration | Secondment Ends
| Task 5.1 | Crop and Pasture Yield and Production modelling | ULIEGE | 13 | IAV | ULIEGE | 9 | 4 | 12
|  |  |  | 14 | IAV | ULIEGE | 33 | 4 | 36
|  |  |  | 10 | ULIEGE | UOH | 6 | 3 | 8
|  |  |  | 23 | UOH | ULIEGE | 13 | 2 | 14
|  |  |  | 24 | UOH | ULIEGE | 25 | 2 | 26
|  |  |  | 9 | UCHILE | ULIEGE | 13 | 2 | 14
|  |  |  | 6 | UOH | ULIEGE | 25 | 2 | 26
|  |  |  | 12 | ULIEGE | UCHILE | 9 | 4 | 12
|  |  |  | 3 | INRA | ULIEGE | 4 | 2 | 5
| Summary | Task 5.1 |  |  |  |  | 4 | 25 | 36
| Task 5.2 | Crop yield modelling under different climate scenarios and economic contexts | ULIEGE | 15 | IAV | ULIEGE | 21 | 4 | 24
|  |  |  | 13 | ULIEGE | INRA | 10 | 3 | 12
|  |  |  | 9 | UOH | ULIEGE | 23 | 2 | 24
|  |  |  | 12 | UOH | ULIEGE | 13 | 2 | 14
|  |  |  | 13 | UOH | ULIEGE | 13 | 2 | 14
|  |  |  | 26 | UOH | ULIEGE | 14 | 3 | 16
|  |  |  | 6 | UCHILE | ULIEGE | 13 | 2 | 14
|  |  |  | 2 | INRA | ULIEGE | 3 | 2 | 4
| Summary | Task 5.2 |  |  |  |  | 3 | 20 | 24
| Task 5.3 | Web-GIS platform building for a better communication with decision makers | ULIEGE | 12 | ULIEGE | IAV | 3 | 3 | 5
|  |  |  | 12 | UCHILE | ULIEGE | 9 | 3 | 11
| Summary | Task 5.3 |  |  |  |  | 3 | 6 | 11
| Participating organisation Short Name |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Total Person Months per Participating organisation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary of Tasks Workpackage Number 5
| Task # | Task Name | Starting Month | End Month | PMs per Task
1 | Task 5.1 | Crop and Pasture Yield and Production modelling | 4 | 36 | 25 |  |  | This table is automatically completed once the list of Tasks is entered
2 | Task 5.2 | Crop yield modelling under different climate scenarios and economic contexts | 3 | 24 | 20
3 | Task 5.3 | Web-GIS platform building for a better communication with decision makers | 3 | 11 | 6
3
3
| Totals WP per Task |  | 3 | 36 | 51
| Total Tasks Workpackage Number 5 |  | 3
List of Deliverables
| Deliverable Number | Deliverable Title | WP No. | Lead Beneficiary Short Name | Type | Dissemination Level | Due Date
1 | D5.1 | Updated crop and pasture yield and production systems for at least 2 countries | 5 | ULIEGE | R | PU
2 | D5.2 | Report on the climate change and economy context change impacts on resilience of agriculture for at least two countries in semi-arid areas | 5 | ULIEGE | R | PU
3 | D5.3 | Workshop on ... | 5 | ULIEGE | PDE | PU
4 | D5.4 | Workshop on ... | 5 | ULIEGE | PDE | PU
5 | D5.5 | Training course on ... | 5 | ULIEGE | PDE | PU
6 | D5.6 | Training course on ... | 5 | ULIEGE | PDE | PU
7
8
9
10

## WP6
| Workpackage Number |  | 6
| Task N° | Task Name | Leading Partner | Staff ID | Sending Institution | Seconded to Organisation | Secondment Starting Month | Secondment Duration | Secondment Ends
| Task 6.1 | Methods and tools to improve the assessment and forecasting of production risks taken by farmers | LIST | 14 | UOH | LIEGE | 8 | 1 | 8
|  |  |  | 14 | UOH | LIST | 24 | 3 | 26
|  |  |  | 14 | UOH | LIEGE | 31 | 1 | 31
|  |  |  | 25 | UOH | LIST | 8 | 2 | 9
|  |  |  | 26 | UOH | LIEGE | 31 | 2 | 32
|  |  |  | 12 | IAV | LIEGE | 12 | 1 | 12
|  |  |  | 12 | IAV | LIST | 15 | 1 | 15
|  |  |  | 13 | IAV | LIEGE | 12 | 3 | 14
|  |  |  | 14 | IAV | LIEGE | 12 | 3 | 14
|  |  |  | 8 | ULIEGE | IAV | 10 | 1 | 10
| Summary | Task 6.1 |  |  |  |  | 8 | 18 | 32
| Task 6.2 | Methods and tools to reduce/mitigate production risks | ULIEGE | 16 | UOH | LIST | 8 | 1 | 8
|  |  |  | 16 | UOH | LIEGE | 24 | 3 | 26
|  |  |  | 16 | UOH | LIST | 31 | 1 | 31
|  |  |  | 26 | UOH | LIEGE | 24 | 2 | 25
|  |  |  | 27 | UOH | LIEGE | 31 | 2 | 32
|  |  |  | 12 | IAV | LIEGE | 24 | 1 | 24
|  |  |  | 12 | IAV | LIST | 27 | 1 | 27
|  |  |  | 13 | IAV | LIEGE | 24 | 3 | 26
|  |  |  | 14 | IAV | LIEGE | 24 | 3 | 26
|  |  |  | 8 | ULIEGE | IAV | 22 | 1 | 22
| Summary | Task 6.2 |  |  |  |  | 8 | 18 | 32
| Task 6.3 | Agriculture Risk Management | ULIEGE | 12 | IAV | UOH | 30 | 1 | 30
|  |  |  | 13 | IAV | UOH | 30 | 2 | 31
|  |  |  | 14 | IAV | UOH | 30 | 2 | 31
|  |  |  | 8 | ULIEGE | UOH | 30 | 1 | 30
|  |  |  | 8 | ULIEGE | LIST | 27 | 1 | 27
| Summary | Task 6.3 |  |  |  |  | 27 | 7 | 31
| Participating organisation Short Name |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Total Person Months per Participating organisation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary of Tasks Workpackage Number 6
| Task # | Task Name | Starting Month | End Month | PMs per Task
1 | Task 6.1 | Methods and tools to improve the assessment and forecasting of production risks taken by farmers | 8 | 32 | 18 |  |  | This table is automatically completed once the list of Tasks is entered
2 | Task 6.2 | Methods and tools to reduce/mitigate production risks | 8 | 32 | 18
3 | Task 6.3 | Agriculture Risk Management | 27 | 31 | 7
3
3
| Totals WP per Task |  | 8 | 32 | 43
| Total Tasks Workpackage Number 6 |  | 3
List of Deliverables
| Deliverable Number | Deliverable Title | WP No. | Lead Beneficiary Short Name | Type | Dissemination Level | Due Date
1 | D6.1 | Methods and tools to improve the assessment and forecasting of production risks taken by farmers | 6 |  | R | PU
2 | D6.2 | Methods and tools to reduce/mitigate production risks | 6 |  | R | PU
3 | D6.3 | Agriculture Risk Management | 6 |  | R | PU
4 | D6.4 | Workshop on… | 6 |  | PDE | PU
5 | D6.5 | Workshop on… | 6 |  | PDE | PU
6 | D6.6 | Training Course | 6 |  | PDE | PU
7
8
9
10

## WP7
| Workpackage Number |  | 7
| Task N° | Task Name | Leading Partner | Staff ID | Sending Institution | Seconded to Organisation | Secondment Starting Month | Secondment Duration | Secondment Ends
| Task 7.1 | Dissemination to agricultural technical community | UNIBO | 1 | UNIBO | UOH | 6 | 1 | 6
|  |  |  | 3 | UNIBO | UOH | 12 | 1 | 12
|  |  |  | 6 | UNIBO | UOH | 18 | 1 | 18
|  |  |  | 11 | UNIBO | UOH | 24 | 1 | 24
|  |  |  | 2 | UOH | IRNAS | 10 | 1 | 10
|  |  |  | 3 | UCHILE | UNIFI | 9 | 1 | 9
|  |  |  | 2 | UAV | ULIEGE | 11 | 1 | 11
|  |  |  | 5 | INRA | ULIEGE | 11 | 1 | 11
|  |  |  | 2 | UOH | IRNAS | 10 | 1 | 10
|  |  |  | 3 | UCHILE | UNIFI | 9 | 1 | 9
|  |  |  | 2 | UAV | ULIEGE | 11 | 1 | 11
|  |  |  | 5 | INRA | ULIEGE | 11 | 1 | 11
|  |  |  | 2 | UOH | IRNAS | 10 | 1 | 10
|  |  |  | 3 | UCHILE | UNIFI | 9 | 1 | 9
|  |  |  | 2 | UAV | ULIEGE | 11 | 1 | 11
|  |  |  | 5 | INRA | ULIEGE | 11 | 1 | 11
| Summary | Task 7.1 |  |  |  |  | 6 | 16 | 24
| Task 7.2 | Increasing Awareness of Farmers | ULIEGE | 1 | ULIEGE | UOH | 6 | 1 | 6
|  |  |  | 2 | ULIEGE | IAV | 10 | 1 | 10
|  |  |  | 1 | LIST | UCHILE | 18 | 1 | 18
|  |  |  | 2 | LIST | IAAA | 20 | 1 | 20
|  |  |  | 1 | ULIEGE | UOH | 30 | 1 | 30
| Summary | Task 7.2 |  |  |  |  | 6 | 5 | 30
| Task 7.3 | Communicating with Consumer Organisations | ULIEGE | 1 | LIST | UCHILE | 4 | 1 | 4
| Summary | Task 7.3 |  |  |  |  | 4 | 1 | 4
| Task 7.4 | Regulations for a Resilient Agriculture | LIST
| Summary | Task 7.4 |  |  |  |  | 0 | 0 | 0
| Task 7.5 | Products and Services for a Resilient Agriculture | AGROP | 1 | AGROP | UOH | 5 | 1 | 5
|  |  |  | 2 | AGROP | AURA | 5 | 1 | 5
|  |  |  | 1 | AURA | AGROP | 9 | 1 | 9
|  |  |  | 2 | AURA | AGROP | 9 | 1 | 9
|  |  |  | 1 | AGROP | UOH | 17 | 1 | 17
|  |  |  | 2 | AGROP | AURA | 17 | 1 | 17
| Summary | Task 7.5 |  |  |  |  | 5 | 6 | 17
| Task 7.6 | Fostering Open Innovation | ULIEGE | 2 | ULIEGE | UOH | 12 | 2 | 13
|  |  |  | 2 | ULIEGE | UOH | 24 | 2 | 25
|  |  |  | 2 | ULIEGE | UCHILE | 32 | 2 | 33
|  |  |  | 24 | UOH | ULIEGE | 9 | 1 | 9
|  |  |  | 9 | UCHILE | ULIEGE | 9 | 1 | 9
| Summary | Task 7.6 |  |  |  |  | 9 | 8 | 33
| Participating organisation Short Name |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Total Person Months per Participating organisation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary of Tasks Workpackage Number 7
| Task # | Task Name | Starting Month | End Month | PMs per Task
1 | Task 7.1 | Dissemination to agricultural technical community | 6 | 24 | 16 |  |  | This table is automatically completed once the list of Tasks is entered
2 | Task 7.2 | Increasing Awareness of Farmers | 6 | 30 | 5
3 | Task 7.3 | Communicating with Consumer Organisations | 4 | 4 | 1
4 | Task 7.4 | Regulations for a Resilient Agriculture | 0 | 0 | 0
5 | Task 7.5 | Products and Services for a Resilient Agriculture | 5 | 17 | 6
6 | Task 7.6 | Fostering Open Innovation | 9 | 33 | 8
| Totals WP per Task |  | 0 | 33 | 36
| Total Tasks Workpackage Number 7 |  | 6
List of Deliverables
| Deliverable Number | Deliverable Title | WP No. | Lead Beneficiary Short Name | Type | Dissemination Level | Due Date
1 | D7.1 | Project’s Website. | 7 | ULIEGE | OTHER | PU | 4
2 | D7.2 | Dissemination Activities Report I | 7 | ULIEGE | R | PU | 12
3 | D7.3 | Dissemination Activities Report II | 7 | ULIEGE | R | PU | 25
4 | D7.4 | Dissemination Activities Report III | 7 | ULIEGE | R | PU | 36
5 | D7.5 | Regulations for a Resilient Agriculture: Comparative Study | 7 | ULIEGE | R | PU | 23
6 | D7.6 | An Open Innovation Strategy for a Resilient Agricuture | 7 | ULIEGE | R | PU | 33
7
8
9
10

## GANTT
This Gantt Chart is automatically built once the Tasks are entered
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36
WP1
Task 1.1 | bar: M1 to M21; M23 to M35
Task 1.2 | bar: M1; M21
Task 1.3 | bar: M2; M6 to M8; M10 to M11; M13 to M26; M28 to M30
0
0
WP2
Task 2.1
Task 2.2 | bar: M23; M25; M28
Task 2.3
Task 2.4
Task 2.5
WP3
Task 3.1 | bar: M3 to M8
Task 3.2 | bar: M6 to M19
Task 3.3 | bar: M8; M17 to M18; M20 to M26; M28
WP4
Task 4.1 | bar: M1 to M11; M13 to M29
Task 4.2 | bar: M5 to M9; M12
Task 4.3 | bar: M1 to M2; M4 to M5; M7 to M13; M15 to M28
Task 4.4
Totals WP per Task
WP5
Task 5.1 | bar: M4 to M32; M34 to M36
Task 5.2 | bar: M3 to M12; M14 to M24
Task 5.3 | bar: M3 to M9; M11
0
0
WP6
Task 6.1 | bar: M8 to M13; M15 to M20; M22 to M32
Task 6.2 | bar: M8 to M20; M22 to M32
Task 6.3 | bar: M27 to M31
0
0
WP7
Task 7.1 | bar: M6 to M24
Task 7.2 | bar: M6 to M30
Task 7.3 | bar: M4
Task 7.4
Task 7.5 | bar: M5 to M17
Task 7.6 | bar: M9 to M33

## Table A3.2
Table A3.2 Summary of Secondments per participant (Beneficiary + Partner Organisations)
Participant Number | Organisation Short Name | Country | Academic | Number of Secondments | Person-months | Estimated budget support (whole duration of the project) |  |  |  | Requested EU Contribution
[6 empty] | Staff member costs | Research, training and networking costs | Management and indirect costs | Total
1 | ULIEGE | BE | Yes | 17 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
2 | UOH | CL | Yes | 43 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
3 | IAV | MA | Yes | 22 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## List of Secondments
WP N* | Task N° | Task Name | Leading Partner | Staff ID | Sending Institution | Seconded to Organisation | Secondment Starting Month | Secondment Duration | Secondment Ends | Description
1 | Task 1.1 | Coordination | ULIEGE | 1 | UOH | ULIEGE | 1 | 1 | 1 | UOH Coordinator travels to Liege for KoM
1 | Task 1.1 | Coordination | ULIEGE | 5 | UCHILE | ULIEGE | 1 | 1 | 1 | UCHILE Coordinator travels to Liege for KoM
1 | Task 1.1 | Coordination | ULIEGE | 1 | AURA | ULIEGE | 1 | 1 | 1 | AURA Coordinator travels to Liege for KoM
1 | Task 1.1 | Coordination | ULIEGE | 1 | IAAA | ULIEGE | 1 | 1 | 1 | IAAA Coordinator travels to Liege for KoM
1 | Task 1.1 | Coordination | ULIEGE | 1 | INRA | ULIEGE | 1 | 1 | 1 | INRA-M Coordinator travels to Liege for KoM
1 | Task 1.1 | Coordination | ULIEGE | 1 | UAV | ULIEGE | 1 | 1 | 1 | UAV Coordinator travels to Liege for KoM
1 | Task 1.1 | Coordination | ULIEGE | 1 | UOH | ULIEGE | 13 | 1 | 13 | UOH Coordinator travels to Bologna and Brussels for Review Meeting
1 | Task 1.1 | Coordination | ULIEGE | 5 | UCHILE | ULIEGE | 13 | 1 | 13 | UCHILE Coordinator travels to Bologna and Brussels for Review Meeting
1 | Task 1.1 | Coordination | ULIEGE | 1 | AURA | ULIEGE | 13 | 1 | 13 | AURA Coordinator travels to Bologna and Brussels for Review Meeting
1 | Task 1.1 | Coordination | ULIEGE | 1 | IAAA | ULIEGE | 13 | 1 | 13 | IAAA Coordinator travels to Bologna and Brussels for Review Meeting
1 | Task 1.1 | Coordination | ULIEGE | 1 | INRA | ULIEGE | 13 | 1 | 13 | INRA-M Coordinator travels to Bologna and Brussels for Review Meeting
1 | Task 1.1 | Coordination | ULIEGE | 1 | UAV | ULIEGE | 13 | 1 | 13 | UAV Coordinator travels to Bologna and Brussels for Review Meeting
1 | Task 1.1 | Coordination | ULIEGE | 1 | UOH | ULIEGE | 25 | 1 | 25 | UOH Coordinator travels to Bologna and Brussels for Review Meeting
1 | Task 1.1 | Coordination | ULIEGE | 5 | UCHILE | ULIEGE | 36 | 1 | 36 | UCHILE Coordinator travels to Bologna and Brussels for Review Meeting
1 | Task 1.1 | Coordination | ULIEGE | 1 | AURA | ULIEGE | 36 | 1 | 36 | AURA Coordinator travels to Bologna and Brussels for Review Meeting
1 | Task 1.1 | Coordination | ULIEGE | 1 | IAAA | ULIEGE | 36 | 1 | 36 | IAAA Coordinator travels to Bologna and Brussels for Review Meeting
1 | Task 1.1 | Coordination | ULIEGE | 1 | INRA | ULIEGE | 36 | 1 | 36 | INRA-M Coordinator travels to Bologna and Brussels for Review Meeting
1 | Task 1.1 | Coordination | ULIEGE | 1 | UAV | ULIEGE | 36 | 1 | 36 | UAV Coordinator travels to Bologna and Brussels for Review Meeting
1 | Task 1.1 | Coordination | ULIEGE
1 | Task 1.2 | Financial Administration | ULIEGE | 25 | UOH | ULIEGE | 1 | 1 | 1 | UOH Financial Officer travels to Liege for Project Management and Financials training
1 | Task 1.2 | Financial Administration | ULIEGE | 10 | UCHILE | ULIEGE | 1 | 1 | 1 | UCHILE Financial Officer travels to Liege for Project Management and Financials training
1 | Task 1.2 | Financial Administration | ULIEGE | 1 | AURA | ULIEGE | 1 | 1 | 1 | AURA Financial Officer travels to Liege for Project Management and Financials training
1 | Task 1.2 | Financial Administration | ULIEGE | 1 | IAAA | ULIEGE | 1 | 1 | 1 | IAAA Financial Officer travels to Liege for Project Management and Financials training
1 | Task 1.2 | Financial Administration | ULIEGE | 1 | INRA | ULIEGE | 1 | 1 | 1 | INRA-M Financial Officer travels to Liege for KoM
1 | Task 1.2 | Financial Administration | ULIEGE | 1 | UAV | ULIEGE | 1 | 1 | 1 | UAV Financial Officer travels to Liege for Project Management and Financials training
1 | Task 1.2 | Financial Administration | ULIEGE | 0 | 0 | 0 | 0 | 0
1 | Task 1.3 | Deliverables, Milestones and Indicators control | ULIEGE | 1 | ULIEGE | UOH | 6 | 1 | 6 | Coordinator travles to Chile for Project Management activities
1 | Task 1.3 | Deliverables, Milestones and Indicators control | ULIEGE | 1 | ULIEGE | IAV | 18 | 1 | 18 | Coordinator travles to Morocco for Project Management activities
1 | Task 1.3 | Deliverables, Milestones and Indicators control | ULIEGE | 1 | ULIEGE | AURA | 30 | 1 | 30 | Coordinator travles to Argentina for Project Management activities
1 | Task 1.3 | Deliverables, Milestones and Indicators control | ULIEGE | 0 | 0 | 0 | 0 | 0
1 | Task 1.3 | Deliverables, Milestones and Indicators control | ULIEGE | 0 | 0 | 0 | 0 | 0
1 | Task 1.3 | Deliverables, Milestones and Indicators control | ULIEGE | 0 | 0 | 0 | 0 | 0
1 | Task 1.3 | Deliverables, Milestones and Indicators control | ULIEGE | 0 | 0 | 0 | 0 | 0
2 | Task 2.1 | Production and characterization of sludge-based biochar, and its use in constructed wetland pilot systems | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.1 | Production and characterization of sludge-based biochar, and its use in constructed wetland pilot systems | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.1 | Production and characterization of sludge-based biochar, and its use in constructed wetland pilot systems | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.1 | Production and characterization of sludge-based biochar, and its use in constructed wetland pilot systems | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.1 | Production and characterization of sludge-based biochar, and its use in constructed wetland pilot systems | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.1 | Production and characterization of sludge-based biochar, and its use in constructed wetland pilot systems | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.1 | Production and characterization of sludge-based biochar, and its use in constructed wetland pilot systems | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.2 | Analysis and monitoring of the system efficiency and the water quality | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.2 | Analysis and monitoring of the system efficiency and the water quality | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.2 | Analysis and monitoring of the system efficiency and the water quality | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.2 | Analysis and monitoring of the system efficiency and the water quality | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.2 | Analysis and monitoring of the system efficiency and the water quality | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.2 | Analysis and monitoring of the system efficiency and the water quality | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.2 | Analysis and monitoring of the system efficiency and the water quality | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.3 | Food analysis for the assessment of food safety and quality | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.3 | Food analysis for the assessment of food safety and quality | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.3 | Food analysis for the assessment of food safety and quality | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.3 | Food analysis for the assessment of food safety and quality | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.3 | Food analysis for the assessment of food safety and quality | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.3 | Food analysis for the assessment of food safety and quality | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.3 | Food analysis for the assessment of food safety and quality | UNIFI | 0 | 0 | 0 | 0 | 0
2 | Task 2.4 | Development of mathematical models for optimization involving uncertainty for recycled water and sustainable water management with a focus on irrigation use | UOH | 0 | 0 | 0 | 0 | 0
2 | Task 2.4 | Development of mathematical models for optimization involving uncertainty for recycled water and sustainable water management with a focus on irrigation use | UOH | 0 | 0 | 0 | 0 | 0
2 | Task 2.4 | Development of mathematical models for optimization involving uncertainty for recycled water and sustainable water management with a focus on irrigation use | UOH | 0 | 0 | 0 | 0 | 0
2 | Task 2.4 | Development of mathematical models for optimization involving uncertainty for recycled water and sustainable water management with a focus on irrigation use | UOH | 0 | 0 | 0 | 0 | 0
2 | Task 2.4 | Development of mathematical models for optimization involving uncertainty for recycled water and sustainable water management with a focus on irrigation use | UOH | 0 | 0 | 0 | 0 | 0
2 | Task 2.4 | Development of mathematical models for optimization involving uncertainty for recycled water and sustainable water management with a focus on irrigation use | UOH | 0 | 0 | 0 | 0 | 0
2 | Task 2.4 | Development of mathematical models for optimization involving uncertainty for recycled water and sustainable water management with a focus on irrigation use | UOH | 0 | 0 | 0 | 0 | 0
2 | Task 2.5 | Development of stochastic optimal control schemes for management recycled water and sustainable water management for irrigation use | UOH | 0 | 0 | 0 | 0 | 0
2 | Task 2.5 | Development of stochastic optimal control schemes for management recycled water and sustainable water management for irrigation use | UOH | 0 | 0 | 0 | 0 | 0
2 | Task 2.5 | Development of stochastic optimal control schemes for management recycled water and sustainable water management for irrigation use | UOH | 0 | 0 | 0 | 0 | 0
2 | Task 2.5 | Development of stochastic optimal control schemes for management recycled water and sustainable water management for irrigation use | UOH | 0 | 0 | 0 | 0 | 0
2 | Task 2.5 | Development of stochastic optimal control schemes for management recycled water and sustainable water management for irrigation use | UOH | 0 | 0 | 0 | 0 | 0
2 | Task 2.5 | Development of stochastic optimal control schemes for management recycled water and sustainable water management for irrigation use | UOH | 0 | 0 | 0 | 0 | 0
2 | Task 2.5 | Development of stochastic optimal control schemes for management recycled water and sustainable water management for irrigation use | UOH | 0 | 0 | 0 | 0 | 0
3 | Task 3.1 | Selection and description of degraded soils | IRNAS | 1 | UOH | IRNAS | 3 | 1 | 3
3 | Task 3.1 | Selection and description of degraded soils | IRNAS | 1 | IRNAS | UOH | 6 | 1 | 6
3 | Task 3.1 | Selection and description of degraded soils | IRNAS | 3 | IRNAS | UOH | 6 | 3 | 8
3 | Task 3.1 | Selection and description of degraded soils | IRNAS | 1 | IRNAS | IAV | 4 | 1 | 4
3 | Task 3.1 | Selection and description of degraded soils | IRNAS | 3 | IRNAS | IAV | 4 | 1 | 4
3 | Task 3.1 | Selection and description of degraded soils | IRNAS | 6 | IRNAS | IAV | 4 | 1 | 4
3 | Task 3.1 | Selection and description of degraded soils | IRNAS | 6 | IRNAS | UOH | 6 | 1 | 6
3 | Task 3.2 | Mesocosms, greenhouse and field experiments with soil amendment monitoring | IRNAS | 5 | UOH | IRNAS | 12 | 3 | 14 | Heike, please note changes in Yellow introduced by UOH
3 | Task 3.2 | Mesocosms, greenhouse and field experiments with soil amendment monitoring | IRNAS | 17 | UOH | IRNAS | 12 | 6 | 17
3 | Task 3.2 | Mesocosms, greenhouse and field experiments with soil amendment monitoring | IRNAS | 18 | UOH | IRNAS | 12 | 6 | 17
3 | Task 3.2 | Mesocosms, greenhouse and field experiments with soil amendment monitoring | IRNAS | 19 | UOH | IRNAS | 12 | 6 | 17 | New secondment
3 | Task 3.2 | Mesocosms, greenhouse and field experiments with soil amendment monitoring | IRNAS | 5 | IRNAS | UOH | 17 | 3 | 19
3 | Task 3.2 | Mesocosms, greenhouse and field experiments with soil amendment monitoring | IRNAS | 2 | IRNAS | UOH | 17 | 1 | 17
3 | Task 3.2 | Mesocosms, greenhouse and field experiments with soil amendment monitoring | IRNAS | 7 | IRNAS | UOH | 17 | 1 | 17
3 | Task 3.2 | Mesocosms, greenhouse and field experiments with soil amendment monitoring | IRNAS | 5 | IRNAS | UNIBO | 6 | 1 | 6
3 | Task 3.3 | Robust multi-continental frame network collaboration | IRNAS | 1 | UOH | IRNAS | 18 | 1 | 18
3 | Task 3.3 | Robust multi-continental frame network collaboration | IRNAS | 5 | UOH | IRNAS | 18 | 1 | 18
3 | Task 3.3 | Robust multi-continental frame network collaboration | IRNAS | 17 | UOH | IRNAS | 18 | 1 | 18 | New secondment
3 | Task 3.3 | Robust multi-continental frame network collaboration | IRNAS | 18 | UOH | IRNAS | 18 | 1 | 18
3 | Task 3.3 | Robust multi-continental frame network collaboration | IRNAS | 4 | IRNAS | UOH | 17 | 1 | 17
3 | Task 3.3 | Robust multi-continental frame network collaboration | IRNAS | 3 | IRNAS | UOH | 28 | 1 | 28
3 | Task 3.3 | Robust multi-continental frame network collaboration | IRNAS | 1 | IRNAS | UAV | 30 | 1 | 0
4 | Task 4.1 | Monitoring of plant pathogens and pests: Diagnostics and Epidemiology | UNIBO | 1 | UNIBO | UOH | 1 | 1 | 1
4 | Task 4.1 | Monitoring of plant pathogens and pests: Diagnostics and Epidemiology | UNIBO | 3 | UNIBO | UOH | 1 | 1 | 1
4 | Task 4.1 | Monitoring of plant pathogens and pests: Diagnostics and Epidemiology | UNIBO | 6 | UNIBO | UOH | 1 | 1 | 1
4 | Task 4.1 | Monitoring of plant pathogens and pests: Diagnostics and Epidemiology | UNIBO | 8 | IAV | UOH | 1 | 1 | 1
4 | Task 4.1 | Monitoring of plant pathogens and pests: Diagnostics and Epidemiology | UNIBO | 8 | IAV | UOH | 6 | 1 | 6
4 | Task 4.1 | Monitoring of plant pathogens and pests: Diagnostics and Epidemiology | UNIBO | 2 | UOH | UNIBO | 29 | 1 | 29
4 | Task 4.1 | Monitoring of plant pathogens and pests: Diagnostics and Epidemiology | UNIBO | 0 | 0 | 0 | 0 | 0
4 | Task 4.2 | Pathogen detection and identification thorough novel molecular assays | UNIBO | 15 | UOH | UNIBO | 7 | 2 | 8
4 | Task 4.2 | Pathogen detection and identification thorough novel molecular assays | UNIBO | 21 | UOH | UNIBO | 5 | 2 | 6
4 | Task 4.2 | Pathogen detection and identification thorough novel molecular assays | UNIBO | 1 | IAV | UNIBO | 6 | 4 | 9
4 | Task 4.2 | Pathogen detection and identification thorough novel molecular assays | UNIBO | 2 | IAV | UNIBO | 8 | 2 | 9
4 | Task 4.2 | Pathogen detection and identification thorough novel molecular assays | UNIBO | 0 | 0 | 0 | 0 | 0
4 | Task 4.2 | Pathogen detection and identification thorough novel molecular assays | UNIBO | 0 | 0 | 0 | 0 | 0
4 | Task 4.2 | Pathogen detection and identification thorough novel molecular assays | UNIBO | 0 | 0 | 0 | 0 | 0
4 | Task 4.3 | Monitoring of plant pests: detection and identification | 0 | 11 | UNIBO | UOH | 1 | 1 | 1
4 | Task 4.3 | Monitoring of plant pests: detection and identification | 0 | 11 | UNIBO | UOH | 1 | 1 | 1
4 | Task 4.3 | Monitoring of plant pests: detection and identification | 0 | 10 | UOH | UNIBO | 6 | 2 | 7
4 | Task 4.3 | Monitoring of plant pests: detection and identification | 0 | 10 | UOH | UNIBO | 29 | 1 | 29
4 | Task 4.3 | Monitoring of plant pests: detection and identification | 0 | 14 | UOH | UNIBO | 19 | 1 | 19
4 | Task 4.3 | Monitoring of plant pests: detection and identification | 0 | 4 | INRA | UOH | 6 | 1 | 6
4 | Task 4.3 | Monitoring of plant pests: detection and identification | 0 | 2 | IAV | UNIBO | 12 | 2 | 13
4 | Task 4.3 | Monitoring of plant pests: detection and identification | 0 | 4 | IAV | UNIBO | 18 | 2 | 19
4 | Task 4.4 | Integrated pathogen/pest management with biocontrol agents (BCA): sustainable control methods for a resilient agriculture | UNIBO | 1 | UNIBO | UOH | 24 | 1 | 24
4 | Task 4.4 | Integrated pathogen/pest management with biocontrol agents (BCA): sustainable control methods for a resilient agriculture | UNIBO | 3 | UNIBO | UOH | 24 | 1 | 24
4 | Task 4.4 | Integrated pathogen/pest management with biocontrol agents (BCA): sustainable control methods for a resilient agriculture | UNIBO | 6 | UNIBO | UOH | 24 | 1 | 24
4 | Task 4.4 | Integrated pathogen/pest management with biocontrol agents (BCA): sustainable control methods for a resilient agriculture | UNIBO | 2 | IAV | UNIBO | 12 | 2 | 13
4 | Task 4.4 | Integrated pathogen/pest management with biocontrol agents (BCA): sustainable control methods for a resilient agriculture | UNIBO | 2 | IAV | UNIBO | 12 | 2 | 13
4 | Task 4.4 | Integrated pathogen/pest management with biocontrol agents (BCA): sustainable control methods for a resilient agriculture | UNIBO | 15 | UOH | UNIBO | 29 | 2 | 30
4 | Task 4.4 | Integrated pathogen/pest management with biocontrol agents (BCA): sustainable control methods for a resilient agriculture | UNIBO | 20 | UOH | UNIBO | 5 | 2 | 6
4 | Task 4.4 | Integrated pathogen/pest management with biocontrol agents (BCA): sustainable control methods for a resilient agriculture | UNIBO | 4 | INRA | UOH | 24 | 1 | 24
4 | Task 4.4 | Integrated pathogen/pest management with biocontrol agents (BCA): sustainable control methods for a resilient agriculture | UNIBO | 8 | INRA | UOH | 24 | 1 | 24
4 | Task 4.4 | Integrated pathogen/pest management with biocontrol agents (BCA): sustainable control methods for a resilient agriculture | UNIBO | 8 | INRA | UOH | 30 | 1 | 30
4 | Task 4.4 | Integrated pathogen/pest management with biocontrol agents (BCA): sustainable control methods for a resilient agriculture | UNIBO | 4 | INRA | UOH | 30 | 1 | 30
5 | Task 5.1 | Crop and Pasture Yield and Production modelling | ULIEGE | 13 | IAV | ULIEGE | 9 | 4 | 12 | Phd-IAV
5 | Task 5.1 | Crop and Pasture Yield and Production modelling | ULIEGE | 14 | IAV | ULIEGE | 33 | 4 | 36 | Phd-IAV
5 | Task 5.1 | Crop and Pasture Yield and Production modelling | ULIEGE | 10 | ULIEGE | UOH | 6 | 3 | 8 | M. Lang
5 | Task 5.1 | Crop and Pasture Yield and Production modelling | ULIEGE | 23 | UOH | ULIEGE | 13 | 2 | 14 | PDoc1-UoH
5 | Task 5.1 | Crop and Pasture Yield and Production modelling | ULIEGE | 24 | UOH | ULIEGE | 25 | 2 | 26
5 | Task 5.1 | Crop and Pasture Yield and Production modelling | ULIEGE | 9 | UCHILE | ULIEGE | 13 | 2 | 14
5 | Task 5.1 | Crop and Pasture Yield and Production modelling | ULIEGE | 24 | UOH | ULIEGE | 25 | 2 | 26 | PhD2-UoH
5 | Task 5.1 | Crop and Pasture Yield and Production modelling | ULIEGE | 12 | ULIEGE | UCHILE | 9 | 4 | 12 | PhD1-ULIEGE
5 | Task 5.1 | Crop and Pasture Yield and Production modelling | ULIEGE | 3 | INRA | ULIEGE | 4 | 2 | 5 | X1 INRA-M
5 | Task 5.2 | Crop yield modelling under different climate scenarios and economic contexts | ULIEGE | 15 | IAV | ULIEGE | 21 | 4 | 24
5 | Task 5.2 | Crop yield modelling under different climate scenarios and economic contexts | ULIEGE | 13 | ULIEGE | INRA | 10 | 3 | 12
5 | Task 5.2 | Crop yield modelling under different climate scenarios and economic contexts | ULIEGE | 9 | UOH | ULIEGE | 23 | 2 | 24
5 | Task 5.2 | Crop yield modelling under different climate scenarios and economic contexts | ULIEGE | 12 | UOH | ULIEGE | 13 | 2 | 14
5 | Task 5.2 | Crop yield modelling under different climate scenarios and economic contexts | ULIEGE | 13 | UOH | ULIEGE | 13 | 2 | 14
5 | Task 5.2 | Crop yield modelling under different climate scenarios and economic contexts | ULIEGE | 26 | UOH | ULIEGE | 14 | 3 | 16
5 | Task 5.2 | Crop yield modelling under different climate scenarios and economic contexts | ULIEGE | 6 | UCHILE | ULIEGE | 13 | 2 | 14
5 | Task 5.2 | Crop yield modelling under different climate scenarios and economic contexts | ULIEGE | 2 | INRA | ULIEGE | 3 | 2 | 4
5 | Task 5.3 | Web-GIS platform building for a better communication with decision makers | ULIEGE | 12 | ULIEGE | IAV | 3 | 3 | 5
5 | Task 5.3 | Web-GIS platform building for a better communication with decision makers | ULIEGE | 12 | UCHILE | ULIEGE | 9 | 3 | 11 | Ph.D. student specializing in Web GIS
5 | Task 5.3 | Web-GIS platform building for a better communication with decision makers | ULIEGE | 0 | 0 | 0 | 0 | 0
5 | Task 5.3 | Web-GIS platform building for a better communication with decision makers | ULIEGE | 0 | 0 | 0 | 0 | 0
5 | Task 5.3 | Web-GIS platform building for a better communication with decision makers | ULIEGE | 0 | 0 | 0 | 0 | 0
5 | Task 5.3 | Web-GIS platform building for a better communication with decision makers | ULIEGE | 0 | 0 | 0 | 0 | 0
5 | Task 5.3 | Web-GIS platform building for a better communication with decision makers | ULIEGE | 0 | 0 | 0 | 0 | 0
6 | Task 6.1 | Methods and tools to improve the assessment and forecasting of production risks taken by farmers | LIST | 14 | UOH | LIEGE | 8 | 1 | 8
6 | Task 6.1 | Methods and tools to improve the assessment and forecasting of production risks taken by farmers | LIST | 14 | UOH | LIST | 24 | 3 | 26
6 | Task 6.1 | Methods and tools to improve the assessment and forecasting of production risks taken by farmers | LIST | 14 | UOH | LIEGE | 31 | 1 | 31
6 | Task 6.1 | Methods and tools to improve the assessment and forecasting of production risks taken by farmers | LIST | 25 | UOH | LIST | 8 | 2 | 9
6 | Task 6.1 | Methods and tools to improve the assessment and forecasting of production risks taken by farmers | LIST | 26 | UOH | LIEGE | 31 | 2 | 32
6 | Task 6.1 | Methods and tools to improve the assessment and forecasting of production risks taken by farmers | LIST | 12 | IAV | LIEGE | 12 | 1 | 12
6 | Task 6.1 | Methods and tools to improve the assessment and forecasting of production risks taken by farmers | LIST | 13 | IAV | LIEGE | 12 | 3 | 14
6 | Task 6.2 | Methods and tools to reduce/mitigate production risks | ULIEGE | 16 | UOH | LIST | 8 | 1 | 8
6 | Task 6.2 | Methods and tools to reduce/mitigate production risks | ULIEGE | 16 | UOH | LIEGE | 24 | 3 | 26
6 | Task 6.2 | Methods and tools to reduce/mitigate production risks | ULIEGE | 16 | UOH | LIST | 31 | 1 | 31
6 | Task 6.2 | Methods and tools to reduce/mitigate production risks | ULIEGE | 26 | UOH | LIEGE | 24 | 2 | 25
6 | Task 6.2 | Methods and tools to reduce/mitigate production risks | ULIEGE | 27 | UOH | LIEGE | 31 | 2 | 32
6 | Task 6.2 | Methods and tools to reduce/mitigate production risks | ULIEGE | 12 | IAV | LIEGE | 24 | 1 | 24
6 | Task 6.2 | Methods and tools to reduce/mitigate production risks | ULIEGE | 13 | IAV | LIEGE | 24 | 3 | 26
6 | Task 6.3 | Agriculture Risk Management | ULIEGE | 12 | IAV | UOH | 30 | 1 | 30
6 | Task 6.3 | Agriculture Risk Management | ULIEGE | 13 | IAV | UOH | 30 | 2 | 31
6 | Task 6.3 | Agriculture Risk Management | ULIEGE | 14 | IAV | UOH | 30 | 2 | 31
6 | Task 6.3 | Agriculture Risk Management | ULIEGE | 8 | ULIEGE | UOH | 30 | 1 | 30
6 | Task 6.3 | Agriculture Risk Management | ULIEGE | 8 | ULIEGE | LIST | 27 | 1 | 27
6 | Task 6.3 | Agriculture Risk Management | ULIEGE | 0 | 0 | 0 | 0 | 0
6 | Task 6.3 | Agriculture Risk Management | ULIEGE | 0 | 0 | 0 | 0 | 0
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 1 | UNIBO | UOH | 6 | 1 | 6 | Seminars planned by WP4
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 3 | UNIBO | UOH | 12 | 1 | 12 | Seminars planned by WP4
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 6 | UNIBO | UOH | 18 | 1 | 18 | Seminars planned by WP4
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 11 | UNIBO | UOH | 24 | 1 | 24 | Seminars planned by WP4
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 2 | UOH | IRNAS | 10 | 1 | 10 | UOH representative travels to Europe for Conferences Year 1
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 3 | UCHILE | UNIFI | 9 | 1 | 9 | UCHILE representative travels to Europe for Conferences Year 1
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 2 | UAV | ULIEGE | 11 | 1 | 11 | UAV representative travels to Europe for Conferences Year 1
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 5 | INRA | ULIEGE | 11 | 1 | 11 | INRA representative travels to Europe for Conferences Year 1
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 2 | UOH | IRNAS | 10 | 1 | 10 | UOH representative travels to Europe for Conferences Year 2
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 3 | UCHILE | UNIFI | 9 | 1 | 9 | UCHILE representative travels to Europe for Conferences Year 2
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 2 | UAV | ULIEGE | 11 | 1 | 11 | UAV representative travels to Europe for Conferences Year 2
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 5 | INRA | ULIEGE | 11 | 1 | 11 | INRA representative travels to Europe for Conferences Year 2
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 2 | UOH | IRNAS | 10 | 1 | 10 | UOH representative travels to Europe for Conferences Year 3
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 3 | UCHILE | UNIFI | 9 | 1 | 9 | UCHILE representative travels to Europe for Conferences Year 3
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 2 | UAV | ULIEGE | 11 | 1 | 11 | UAV representative travels to Europe for Conferences Year 3
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 5 | INRA | ULIEGE | 11 | 1 | 11 | INRA representative travels to Europe for Conferences Year 3
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 0 | 0 | 0 | 0 | 0
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 0 | 0 | 0 | 0 | 0
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 0 | 0 | 0 | 0 | 0
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 0 | 0 | 0 | 0 | 0
7 | Task 7.1 | Dissemination to agricultural technical community | UNIBO | 0 | 0 | 0 | 0 | 0
7 | Task 7.2 | Increasing Awareness of Farmers | ULIEGE | 1 | ULIEGE | UOH | 6 | 1 | 6 | B. Tychon travels to UOH for Workshop on Resilience for farmers' organisations. Workshop is sincronized with internal WP4
7 | Task 7.2 | Increasing Awareness of Farmers | ULIEGE | 2 | ULIEGE | IAV | 10 | 1 | 10 | B. Tychon travels to IAV for Workshop on Resilience for farmers' organisations. (Secondment is Split during the 3 years)
7 | Task 7.2 | Increasing Awareness of Farmers | ULIEGE | 1 | LIST | UCHILE | 18 | 1 | 18 | Lucien Hoffman or Researchers travels to UCHILE for Workshop on Resilience for farmers' organisations centered in risks
7 | Task 7.2 | Increasing Awareness of Farmers | ULIEGE | 2 | LIST | IAAA | 20 | 1 | 20 | Lucien Hoffman or Researchers travels to IAAA for Workshop on Resilience for farmers' organisations centered in risks
7 | Task 7.2 | Increasing Awareness of Farmers | ULIEGE | 1 | ULIEGE | UOH | 30 | 1 | 30 | B. Tychon travels to UOH for Workshop on Resilience for farmers' organisations.
7 | Task 7.2 | Increasing Awareness of Farmers | ULIEGE | 0 | 0 | 0 | 0 | 0
7 | Task 7.2 | Increasing Awareness of Farmers | ULIEGE | 0 | 0 | 0 | 0 | 0
7 | Task 7.3 | Communicating with Consumer Organisations | ULIEGE | 1 | LIST | UCHILE | 4 | 1 | 4
7 | Task 7.3 | Communicating with Consumer Organisations | ULIEGE | 0 | 0 | 0 | 0 | 0
7 | Task 7.3 | Communicating with Consumer Organisations | ULIEGE | 0 | 0 | 0 | 0 | 0
7 | Task 7.3 | Communicating with Consumer Organisations | ULIEGE | 0 | 0 | 0 | 0 | 0
7 | Task 7.3 | Communicating with Consumer Organisations | ULIEGE | 0 | 0 | 0 | 0 | 0
7 | Task 7.3 | Communicating with Consumer Organisations | ULIEGE | 0 | 0 | 0 | 0 | 0
7 | Task 7.3 | Communicating with Consumer Organisations | ULIEGE | 0 | 0 | 0 | 0 | 0
7 | Task 7.4 | Regulations for a Resilient Agriculture | LIST | 0 | 0 | 0 | 0 | 0 | 0
7 | Task 7.4 | Regulations for a Resilient Agriculture | LIST | 0 | 0 | 0 | 0 | 0 | 0
7 | Task 7.4 | Regulations for a Resilient Agriculture | LIST | 0 | 0 | 0 | 0 | 0
7 | Task 7.4 | Regulations for a Resilient Agriculture | LIST | 0 | 0 | 0 | 0 | 0
7 | Task 7.4 | Regulations for a Resilient Agriculture | LIST | 0 | 0 | 0 | 0 | 0
7 | Task 7.4 | Regulations for a Resilient Agriculture | LIST | 0 | 0 | 0 | 0 | 0
7 | Task 7.4 | Regulations for a Resilient Agriculture | LIST | 0 | 0 | 0 | 0 | 0
7 | Task 7.5 | Products and Services for a Resilient Agriculture | AGROP | 1 | AGROP | UOH | 12 | 1 | 5 | Agroptimize travels to Chile / Argentina for Workshop with Businesses end startups
7 | Task 7.5 | Products and Services for a Resilient Agriculture | AGROP | 2 | AGROP | AURA | 12 | 1 | 5 | Agroptimize travels to Chile / Argentina for Workshop with Businesses end startups
7 | Task 7.5 | Products and Services for a Resilient Agriculture | AGROP | 1 | AURA | AGROP | 9 | 1 | 9 | AURAVANT travels to France
7 | Task 7.5 | Products and Services for a Resilient Agriculture | AGROP | 2 | AURA | AGROP | 9 | 1 | 9 | AURAVANT travels to France
7 | Task 7.5 | Products and Services for a Resilient Agriculture | AGROP | 1 | AGROP | UOH | 24 | 1 | 17 | Agroptimize travels to Chile / Argentina for Workshop with Businesses end startups
7 | Task 7.5 | Products and Services for a Resilient Agriculture | AGROP | 2 | AGROP | AURA | 24 | 1 | 17 | Agroptimize travels to Chile / Argentina for Workshop with Businesses end startups
7 | Task 7.5 | Products and Services for a Resilient Agriculture | AGROP | 0 | 0 | 0 | 0 | 0
7 | Task 7.6 | Fostering Open Innovation | ULIEGE | 2 | ULIEGE | UOH | 12 | 2 | 13 | Eric Feller travels to Chile/Argentina
7 | Task 7.6 | Fostering Open Innovation | ULIEGE | 2 | ULIEGE | UOH | 24 | 2 | 25 | Eric Feller travels to Chile/Argentina
7 | Task 7.6 | Fostering Open Innovation | ULIEGE | 2 | ULIEGE | UCHILE | 32 | 2 | 33 | Eric Feller travels to Chile/Argentina
7 | Task 7.6 | Fostering Open Innovation | ULIEGE | 24 | UOH | ULIEGE | 9 | 1 | 9 | UOH Innovation officer travels to Liege
7 | Task 7.6 | Fostering Open Innovation | ULIEGE | 9 | UCHILE | ULIEGE | 9 | 1 | 9 | UCHILE Innovation officer travels to Liege
7 | Task 7.6 | Fostering Open Innovation | ULIEGE | 0 | 0 | 0 | 0 | 0
7 | Task 7.6 | Fostering Open Innovation | ULIEGE | 0 | 0 | 0 | 0 | 0
7 | Task 7.6 | Fostering Open Innovation | ULIEGE | 0 | 0 | 0 | 0 | 0
7 | Task 7.6 | Fostering Open Innovation | ULIEGE | 0 | 0 | 0 | 0 | 0
7 | Task 7.6 | Fostering Open Innovation | ULIEGE | 0 | 0 | 0 | 0 | 0
7 | Task 7.6 | Fostering Open Innovation | ULIEGE | 0 | 0 | 0 | 0 | 0
7 | Task 7.6 | Fostering Open Innovation | ULIEGE | 0 | 0 | 0 | 0 | 0
7 | Task 7.6 | Fostering Open Innovation | ULIEGE | 0 | 0 | 0 | 0 | 0